## Sheet1
Task Name | Status | Start Date | Due Date
Start Meeting to fing idea | Completed | 15/09/2020 | 16/09/2020
Choosing Idea | Completed | 16/09/2020 | 17/09/2020
Brainstorming | Completed | 17/09/2020 | 17/09/2020
Searching about text Classification | Completed | 17/09/2020 | 22/09/2020
Searching about Datasets | Completed | 22/09/2020 | 25/09/2020
Searching about techniques and algorithms | Completed | 25/09/2020 | 29/09/2020
reviewing online related work | Completed | 2020-01-10 | 2020-03-10
Choosing best tools to use | Completed | 2020-03-10 | 2020-04-10
Choosing appropirate datasets | Completed | 2020-04-10 | 2020-06-10
Start writing Survey about our project | Completed | 2020-06-10 | 2020-10-10
Writing about all related work | Completed | 2020-10-10 | 2020-12-10
Preprocessing our datasets | In Progress | 2020-12-10 | 20/4/2021
start designing our models | In Progress | 14/10/2020 | 13/4/2021
training models | In Progress | 18/10/2020 | 17/4/2021
Design Class Diagram | In Progress | 20/10/2020 | 2021-01-05
Design use cases | In Progress | 21/10/2020 | 28/4/2021
Design sequence Diagrams | In Progress | 22/10/2020 | 2021-05-05
Design UI using React | In Progress | 2020-01-11 | 20/5/2021
Implementing Back-End | In Progress | 2020-05-11 | 2021-09-05
Implementing Pre-Trained models | Future Work | 2021-01-04 | 2021-05-04
Testing our models | In Progress | 2021-01-01 | 18/5/2021
Testing our Back end | Future Work | 2021-04-01 | 21/5/2021
Publishing our research | Future Work | 20/1/2021 | 23/5/2021
Deploying our site | Future Work | 24/5/2021 | 25/5/2021