## Sheet1
Task Name | Status | Start Date | Due Date
Start Meeting to find idea | Completed | 15/09/2020 | 16/09/2020
Choosing Idea | Completed | 16/09/2020 | 17/09/2020
Brainstorming | Completed | 17/09/2020 | 17/09/2020
Searching about text Classification | Completed | 17/09/2020 | 22/09/2020
Searching about Datasets | Completed | 22/09/2020 | 25/09/2020
Searching about techniques and algorithms | Completed | 25/09/2020 | 29/09/2020
reviewing online related work | Completed | 2020-01-10 | 2020-03-10
Choosing best tools to use | Completed | 2020-03-10 | 2020-04-10
Choosing appropirate datasets | Completed | 2020-04-10 | 2020-06-10
Start writing Survey about our project | Completed | 2020-06-10 | 2020-10-10
Writing about all related work | Completed | 2020-10-10 | 2020-12-10
Preprocessing our datasets | Completed | 2020-12-10 | 20/4/2021
start designing our models | Completed | 14/10/2020 | 13/4/2021
training models | Completed | 18/10/2020 | 17/4/2021
Design Class Diagram | Completed | 20/10/2020 | 2021-01-05
Design use cases | Completed | 21/10/2020 | 28/4/2021
Design sequence Diagrams | Completed | 22/10/2020 | 2021-05-05
Design UI using React | Completed | 2020-01-11 | 20/5/2021
Implementing Back-End | Completed | 2020-05-11 | 2021-09-05
Implementing Pre-Trained models | Completed | 2021-01-04 | 2021-05-04
Testing our models | Completed | 2021-01-01 | 18/5/2021
Testing our Back end | Completed | 2021-04-01 | 21/5/2021
cleaning the arxiv dataset | Completed | 22/5/2021 | 30/5/2021
Comparing models to choose the best for arxiv | Completed | 2021-07-07 | 13/7/2021
Training on big data(arxiv dataset) | Completed | 13/7/2021 | 15/7/2021
Updating all diagrams with new updates | Completed | 16/7/2021 | 20/7/2021
Publishing our research | Completed | 20/7/2021 | 22/7/2021
Deploying our site | Future Work
Adding all big size models to our web application | Future Work